## Sheet1
Optimistic timeline for a postdoc to build Atlantis model. 2 years, assuming lots of prior modeling has been done in the system.
Assumign postdoc has no other major time commitments, teaching, or classes.
Requires farming out the building of oceanographic input files to ROMS or similar oceanographer (following details in user manual).
Requires some help from local GIS experts and CSIRO Australia GIS experts in building map input files to Atlantis. (see details in user manual).
Requires some hands-on in-person help from an experienced Atlantis user for a couple weeks, especically when doing initial runs at end of year 1.
May require some hands-on tungin from Beth Fulton, in person, for a couple weeks of calibration (first 1/3 of year 2).
Completely based on Isaac's opinion.
| Month | Oceangraphy | Fisheries | Ecology | Map | Writing
Year 1 | 1 | Discuss model geography with oceanographers | Discuss model geography and fleet structure with fisheries experts | Read all relevant ecosytem models; collect all Ecopath/Ecosim/Ecospace analyses. |  | Write methods
Year 1 | 2 | " | " | Discuss model decisions with experts: geography, functioal groups, fleets. |  | "
Year 1 | 3 | Finalize model geography. | Casually begin collecting fishery catch time series, per species and fleet, and time series of abundance data from stock assessment or monitorign | Collect data on species abujdance, life history, diet, migration, etc. ; begin PRM and CDF. |  | "
Year 1 | 4 | Request data from oceanographers (see User Manual) | " | " | Build BGM map input | "
Year 1 | 5 | Oceanographers interpolate ROMS data onto Atlantis grid. | " | " |  | "
Year 1 | 6 | " | " | " |  | "
Year 1 | 7 | oceanography data ready to read into Atlantis. | " | " |  | "
Year 1 | 8 |  | " | Finalize Building Biology rate parameters file (PRM) |  | "
Year 1 | 9 |  | " | Finalize Building Biology initial conditions file (CDF) |  | "
Year 1 | 10 |  | " |  |  | "
Year 1 | 11 |  | Runs with no fishing: Phase I calibration. | Runs with no fishing: Phase I calibration. |  | "
Year 1 | 12 |  | " |  |  | "
Year 2 | 1 |  | Continue " No Fishing" runs; also Build historical fishery input files for Atlantis. |  |  | Write descriptin of unfished Biomass estimates
Year 2 | 2 |  | " |  |  | "
Year 2 | 3 |  | " |  |  | "
Year 2 | 4 |  | Running simple fishery experiments (like F= 0.1, F=0.2, F=0.3, etc.) |  |  | Write description of results of simple fishing policies (F=0.1, F=0.2, F=0.3, etc. )
Year 2 | 5 |  | " |  |  | "
Year 2 | 6 |  | " |  |  | "
Year 2 | 7 |  | Running historical fishery simulations. Also discuss policy / fishery scenarios to test, with experts or stakeholders |  |  | Write description of historical reconstruction runs.
Year 2 | 8 |  | " |  |  | "
Year 2 | 9 |  | " |  |  | "
Year 2 | 10 |  | Possible runs of policy/fishery scenarios (if time allows) |  |  | Write up policy scenario outputs if time allows.
Year 2 | 11 |  | "
Year 2 | 12 |  | " |  |  | "